## Live CP Register
Last updated: 26/04/2024
Change Proposal Reference | Change Proposal Name | Change Description | Link to CP page | Proposer Name | Proposer Company | Lead Analyst | Date Submitted | Change Category | Urgent (Y/N) | Priority Status | Priority Score | Change Path | Responsible Committee | Fuel | Impacted Parties | Proposed Implementation Date | MHHS Design | Last Activity | Last Activity Date | Current Process Stage | Next Activity | Next Activity Due Date | Next Action with Code Manager? | Does this change impact Xoserve ? | Does this change Impact DCC ?
R0006 | Missing Meter Technical Details | On a Change of Supplier, where a new Metering Equipment Manager is appointed by the Gaining supplier (and they are different to the Losing Supplier’s Metering Equipment Manager (MEM)), if the Losing Supplier’s MEM doesn’t receive or respond to the request for Meter Technical Details from the Gaining Supplier’s MEM, they will be unable to provide them to the Gaining Supplier. In the absence of the Meter Technical Details, the Gaining Supplier is unable to set up the Customer’s Account and Billing records, which means that the customer is at risk of not receiving their new bills on time. The Losing supplier may also not receive the final readings and may have to rely on an industry provided estimate, resulting in a possible challenge to that bill and further work to resolve and close the account. | Link | Diane Lyon | Scottish Power Energy Retail | Elise Handy | 2021-09-07 | 2b (Cat 2 products with technical impacts) | No | Low | 98 | Self-Governance | Change Panel | Electricity | Energy Suppliers, Metering Equipment Managers, EES, Data Collectors |  | Y - Interest | Technical Expert Panel decision (R0121) | 2024-04-24 | Final Assessment | Speak with proposer of R0006 | 2024-05-03 |  | N | N
R0037 | Prepayment Credit Balance & Debt Transfer Processes | This Change Proposal seeks to develop an agile, efficient, Consumer-centric solution for the transfer of credit or debt balance as part of a smart prepayment Switch, with aligned improvements to non-smart processes. | Link | Andy Knowles | Utilita | Caroline Freimuller | 2022-03-10 | 1b (Cat 1 products with technical impacts) | No | Medium | 123 | Authority-Approval | Change Panel | Electricity and Gas | Energy Suppliers |  | N | Update to Change Panel to confirm change going on hold due to MHHS code freeze | 2024-04-16 | On Hold | Actions taken away from previous Change Panel, update to be provided on 07/05/2024 and change plan withdrawn | 2024-05-07 |  | Y | Y
R0043 | Commissioning of Works using shared Meter Operator services by the Crowded Meter Room Co-ordinator (CMRC) | Many GB households are currently unable to enjoy the many benefits of smart metering because they live in places where the components of their “Home Area Network” (HAN) – energy meters, in-home devices and communications hub – are too far apart to connect with each other. For many Multi Dwelling Units (MDUs) e.g. flats, Alternative HAN equipment is required, this will involve the additional use of a wired Point to Point (P2P) device that is installed near to the Electricity Smart Meter and connected to the tails of that Smart Meter and at least one further device in the customers premises. Work by Alt HAN Co since 2020, in collaboration with industry has identified the additional challenge posed by 'Crowded Meter Rooms' for the installation of Alt HAN and smart equipment. | Link | David Jones | Alt HanCo | Gemma Dixon | 2022-04-21 | 1b (Cat 1 products with technical impacts) | No | Medium | 118 | Authority-Approval | Change Panel | Electricity | Electricity Suppliers, Distribution Network Operators, Metering Equipment Managers, Data Collectors, Meter Asset Providers | 2024-06-28 | Y - Interest | Authority approval received | 2024-01-15 | Awaiting Implementation | Implementation | 2024-06-28 |  | N | N
R0044 | MHHS Programme Changes required to Central Switching Service | Ofgem’s Electricity Settlement Reform Significant Code Review (SCR) has concluded that settling all electricity consumers on a half-hourly basis would bring net benefits of up to £4.5bn by 2045. Ofgem has therefore concluded that Suppliers should be mandated to settle their electricity customers on a half-hourly basis. Delivering the full solution for Market-wide Half-Hourly Settlement (MHHS) will require a new Smart Data Service which includes a Meter Data Retrieval (MDR) service which will retrieve data directly from smart meters as a new Data Communications Company (DCC) User Role as set out in Smart Energy Code (SEC) Modification Proposal 162 (MP162) ‘SEC changes required to deliver MHHS’ https://smartenergycodecompany.co.uk/modifications/sec-changes-required-to-deliver-mhhs/ There will be a wider set of Retail Energy Code (REC) changes being progressed under the MHHS Programme that will cover all the necessary updates to deliver the MHHS Programme. This REC Change Proposal (CP) has been raised to progress the specific CSS system changes related to the MDR service. An impact assessment is required as early as possible, and the changes progressed and implemented in appropriate timescales, to minimise the risk of CSS changes impacting the critical path of the MHHS Programme. This was the same approach taken in raising MP162 to the SEC in advance of all of the SEC Code Changes being drafted. | Link | Jason Brogden | MHHS Programme | Harriet Truss | 2022-04-29 | 1b (Cat 1 products with technical impacts) | Yes | Medium | 110 | Authority-Approval | Change Panel | Electricity | DCC as CSS Provider, (Distribution Network Operators as ERDS Providers) | MHHS M8 | Y - Conseq | Authority approval received | 2023-02-02 | Awaiting Implementation | Implementation | MHHS M8, 07/03/2025 |  | N | Y
R0048 | DCC Service Organisation Control 2 (SOC2) Assessments | Experience has shown SOC Type 2 to be both inappropriate and costly in the SEC and would be vast over application of assurance within the Switching service now that DCC have a better understanding of the risk profile. Replacing the requirement for a SOC Type 2 security certification with an “independently assured” requirement would allow for a better suited regime to be implemented by the DCC which will allow greater value and assurance. | Link | Cordelia Grey | DCC | Caroline Freimuller | 2022-05-20 | 2a (Cat 2 products without technical impacts) | No | Low | 85 | Self-Governance | Technical Expert Panel | n/a | DCC |  | N | Consultation opened. | 2024-04-26 | Consultation | Consultation closed. | 2024-05-20 |  | Y | Y
R0049 | Intellectual Property Rights and Services Data Main Body changes | The CRS Services IPR provisions in the Code were drafted before designation of v1.0 of the Code and primarily seek to deal with the CRS Services IPR as if it were IPR developed and owned by the CRS Provider or its contractors. In reality, much of the solution is built upon third party-owned software or platforms/services that are available to the market. Notwithstanding certain concessions were drafted in Clause 13.5 of the Code at designation, the scope of CRS Service IPR refers to some now obsolete terms and concepts and ought to be amended to clarify what the CRS Provider actually owns or is responsible for, to alleviate the existing ambiguity. Potential to amend Clause 13 of the Code as proposed in the attached mark-up, with consequential amendments to the associated definitions in Schedule 1 (Interpretation and Definitions). The definition “User” should be deleted from the Code and the defined terms “CSS User” or “REC Service User” (as applicable) used in substitution. | Link | Bradley Baker | DCC | Lydia Bentley | 2022-05-20 | 1a (Cat 1 products without technical impacts) | No | Low | 37 | Self-Governance | Change Panel | n/a | DCC |  | N | DCC to review legal text following review by the Code Manager's legal counsel | 2024-04-12 | Initial Assessment | Code Manager to review Data Communications Company (DCC) comments on draft legal text and decide how to proceed. | 2024-05-03 |  | N | Y
R0053 | 24/7 Emergency Metering Service | Suppliers currently are not required to provide a 24/7 emergency metering service that enables a Consumer to speak to an agent and/or receive a visit from a field operative outside normal business hours when faced with power loss situation relating to a metering issue. This Change Proposal has been raised to assess and consider the options to address this issue. | Link | Bryan Heap | Electricity North West Limited | Sam Briggs | 2022-06-15 | 1a (Cat 1 products without technical impacts) | No | Medium | 128 | Authority-Approval | Change Panel | Electricity | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers |  | N | Meeting with the proposer arranged to discuss next steps 16/11/2023 | 2023-11-16 | On Hold | On hold at the proposers request | 2024-05-03 |  | N | N
R0056 | EES/GES Additional Service Request for Housing Associations to be added to the Data Access Matrix | Housing Associations need to validate supply point information to ensure that they have the most up to date and accurate data against each property in their portfolio and also to complement their internal safety inspection processes. We are requesting that Housing Associations have access to data in EES and GES to understand and confirm which of their properties contain live supply points, the meter locations, asset data and last inspection checks. This will also enable Housing Associations to update the industry where gas safety information is not accurate against their site data. | Link | Fay Morris | Correla Limited | Task Force Elise Handy | 2022-07-05 | 2b (Cat 2 products with technical impacts) | No | Low | 53 | Self-Governance | TBD | Electricity and Gas | EES, GES |  | N | Housing Association have submitted a Data Access Application to receive the standard Housing Association Report in the short term - this is nw in progress with RPA. Awaiting Xoserve to confirm if API was actually built to provide similar information. | 2024-04-17 | Solution Development | Understand from Xoserve if bespoke API already exists and can be used. Confirm progress of request for standard Housing Association report. | 2024-05-03 |  | Y | N
R0060 | ERDS Service Definition time zone correction | This change seeks to specify time zones within the ERDS Service Definition. For example: Data received by the ERDA shall be included within the ERDS Total Daily Processing on the basis that all data received prior to 23:00hrs is made available to the SMRA, EES Provider or CSS Provider (as applicable) by 06:00hrs the following Working Day. Data received after 23:00hrs will be made available to the SMRA, EES Provider or CSS Provider (as applicable) by the second Working Day | Link | Daniel Tadecicco | St Clements | Task Force Elise Handy | 2022-08-11 | 1a (Cat 1 products without technical impacts) | No | Low | 26 | Self-Governance | TBD | Electricity | ERDS, EES |  | Y - Interest | MHHS Programme is investigating the implications of this change. This will determine how it can be progressed. | 2024-03-22 | Initial Assessment | Next steps to be defined. | 2024-05-03 |  | N | Y
R0064 | Creating a Meter Operator Agent and MOCoP Installer | This Change Proposal seeks to clarify the obligations of each type of metering provider by reintroducing this distinction. Prior to Retail Code Consolidation, electricity metering providers were either classified as Meter Operator Agent or MOCOPA Meter Installers. At Retail Code Consolidation these organisations were merged into a new category, Metering Equipment Managers, which also included gas metering providers. Whilst both types of organisation can provide metering services, not all MEM obligations in the REC apply to both organisations. | Link | Anton Moden | Code Manager | Gemma Dixon | 2022-08-22 | 1b (Cat 1 products with technical impacts) | No | Medium | 135 | Self-Governance | Change Panel | Electricity and Gas | Metering Equipment Managers, RECCo, Code Manager, Energy Suppliers, Metering Schemes Auditor | 2024-06-28 | Y - Interest | Final Change Report approval at Change Panel | 2024-02-06 | Awaiting Implementation | Awaiting Implementation | 2024-06-28 |  | N | N
R0069 | Amendments to Sample Access Agreement | A number of Non-Party REC Service Users have entered into an Access Agreement with RECCo under the Code’s Qualification and Maintenance Schedule to obtain access to the CSS and become a CSS User. These Access Agreements are based on the Sample Access Agreement appended to Schedule 9 to the Code, which DCC believes should have been revised to address the issues | Link | Cordelia Grey | DCC | Task Force Caroline Freimuller | 2022-09-02 | 1a (Cat 1 products without technical impacts) | No | Low | 54 | Self-Governance | Performance Assurance Board | Electricity and Gas | DCC |  | N | Legal and DCC confirmed they are happy with legal text changes | 2024-04-23 | Initial Assessment | RPA to provide comments on legal text changes | 2024-04-30 |  | N | Y
R0070 | Provision of Enduring Test Environments | Currently the REC does not require the Central Switching Service (CSS) and Switching Operator (SO) to provide the enduring test environments and test data for use by REC Parties when making necessary system changes for REC Change Proposals or internal system updates. | Link | Beth Brown | Code Manager | James Hardy | 2022-09-09 | 2b (Cat 2 products with technical impacts) | No | Medium | 103 | Self-Governance | Change Panel | Electricity and Gas | CSS Provider, Switching Operator | 2024-06-28 | N | Final Change Report approved at Change Panel | 2024-03-05 | Awaiting Implementation | Awaiting Implementation | 2024-06-28 |  | Y | Y
R0072 | Introduction of a new Meter Asset Condition Code | This change seeks to introduce a new Asset Condition Code where further investigation is required by a DNO where there is suspected asbestos in the metal encased cut-out | Link | Clive Wicks | Consumer | Task Force Elise Handy | 2022-09-22 | 2b (Cat 2 products with technical impacts) | No | Low | 76 | Self-Governance | TBD | Electricity | MEMs and DNOs |  | N | Following RFI, change will be raised at the Cross Code Steering Group for discussion with DCUSA. | 2024-04-02 | Initial Assessment | If DCUSA does not progress this change, it will need to be rejected. | 2024-05-03 |  | N | N
R0076 | DNOs notifying Suppliers about Crossed Meters | The Change seeks to introduce a way for the DNOs to raise a crossed meter issue with the supplier, in a way that directly feeds into the supplier’s list of crossed meter issues. The supplier will be required to feedback progress to the DNO who has raised the issue with them, this should be defined as a process within the REC | Link | Anne-Claire Leydier | UK Power Distribution | Task Force Elise Handy | 2022-10-07 | 2b (Cat 2 products with technical impacts) | No | Low | 83 | Self-Governance | TBD | Electricity | Energy Suppliers, Distribution Network Operators, SDES Provider |  | TBD | Technical Expert Panel approved R0121 for implementation 23/08/2024. | 2024-04-24 | Final Assessment | Speak with proposer regarding withdrawal. | 2024-05-03 |  | N | N
R0080 | Improvements to ‘Failed to Deliver’ CSS Messages | Since Go-Live a large number of messages have been unsuccessfully delivered due to failures of CSS Users gateways, resulting in CSS exhausting the 12-hour retry period. This Change Proposal has been raised to explore and address this issue | Link | Cordelia Grey | DCC | Task Force Elise Handy | 2022-10-27 | 2b (Cat 2 products with technical impacts) | No | Medium | 136 | Self-Governance | TBD | Electricity and Gas | Energy Suppliers, DCC |  | Y - Interest | Re-baselined change plan. | 2024-04-26 | Impact Assessment (REC Party only) | Some clarifications are required based on the Party Impact Assessment responses prior to proceeding to the Preliminary Assessment stage. | 2024-05-10 |  | Y | Y
R0083 | Changes to Supply Number Format for MHHS | This CP to update the Supply Number Format as a result of MHHS change that ill mean some of the data items will no longer be available. This change looks to amend the data items in the top line of the Supply Number. | Link | Andrew Wallace | RECCo | Harriet Truss | 2022-12-02 | 2a (Cat 2 products without technical impacts) | No | High | 158 | Authority-Approval | Change Panel | Electricity | Suppliers, DNOs, TPIs, , EES | MHHS M8 | Y - Conseq | Authority Determination received Approving R0083 | 2023-11-17 | Awaiting Implementation | Implementation | MHHS M8, 07/03/2025 |  | N | N
R0087 | MAP - GES Portfolio Dashboard | This Change Proposal is to look at the possibility of providing a portfolio view for the MAP. | Link | David Newman | Correla Limited on behalf of EON | Task Force Elise Handy | 2022-12-09 | 2b (Cat 2 products with technical impacts) | No | Low | 33 | Self-Governance | TBD | Gas | Meter Asset Providers |  | N | Meeting with MAP & Corella to discuss background and agree next steps | 2024-04-15 | Initial Assessment | Corella to provide summary and costs for E.ON to review, to decide whether or not they want to progress the solution via a brand new API + DDP solution (or instead consider use of existing standard reports). | 2024-05-03 |  | Y | N
R0092 | DCC Service Level Agreements for the Switching Incentive Regime | Requirements for the Central Switching Service (CSS) were identified during the Design, Build and Test Phase of the Ofgem-led Switching Programme as a basis for the procurement of Switching systems. These requirements were later baselined in the REC Service Definitions as Service Level Agreements (SLAs). Following the successful go-live of the CSS, these SLAs merit a review, in order to ensure that they are realistic, given the physical systems design and the actual behaviours of users, compared to the assumptions that were made in the early design phase of the Switching Programme. Such a review of SLAs – with a view to maintaining requirements that provide systems performance levels required by REC Parties and ensuring that relevant performance aspects are being measured, reported on and incentivised – would provide greater clarity to REC parties and more effective performance management of CSS performance. | Link | Cordelia Grey | DCC | Elise Handy | 2023-02-01 | 2a (Cat 2 products without technical impacts) | No | High | 152 | Authority-Approval | Performance Assurance Board | Electricity and Gas | Central Registration Service, CSS Users, Switching Service Providers |  | N | Final Change Report published. | 2024-04-19 | Final Assessment | For decision at Performance Assurance Board | 2024-04-30 |  | Y | Y
R0092A | DCC Service Level Agreements for the Switching Incentive Regime | Requirements for the Central Switching Service (CSS) were identified during the Design, Build and Test Phase of the Ofgem-led Switching Programme as a basis for the procurement of Switching systems. These requirements were later baselined in the REC Service Definitions as Service Level Agreements (SLAs). Following the successful go-live of the CSS, these SLAs merit a review, in order to ensure that they are realistic, given the physical systems design and the actual behaviours of users, compared to the assumptions that were made in the early design phase of the Switching Programme. Such a review of SLAs – with a view to maintaining requirements that provide systems performance levels required by REC Parties and ensuring that relevant performance aspects are being measured, reported on and incentivised – would provide greater clarity to REC parties and more effective performance management of CSS performance. | Link | Elise Handy | Code Manager | Elise Handy | 2024-01-26 | 2a (Cat 2 products without technical impacts) | No | High | 152 | Authority-Approval | Performance Assurance Board | Electricity and Gas | Central Registration Service, CSS Users, Switching Service Providers |  | N | Final Change Report published. | 2024-04-19 | Final Assessment | For decision at Performance Assurance Board | 2024-04-30 |  | Y | Y
R0094 | Clarify obligations on gas meter exchanges that occur close to CoS | This change has been raised to address an issue with the 'Switch with a Concurrent Change of MEM process.'. MEMs are obliged to issue ONJOBs to the CDSP as part of a meter exchange. However, this would not be issued if the MEM has received a de-Appointment flow as part of the Switch. This change proposes to obligate MEMs to issue ONJOBs for any completed meter exchanges, even after receiving a de-Appointment flow. This will ensure accurate Meter Technical Details are available to the gaining Supplier and MEM. | Link | David Morley | Ovo | Task Force Lydia Bentley | 2022-11-29 | 1a (Cat 1 products without technical impacts) | No | Medium | 114 | Self-Governance | Metering Expert Panel | Gas | Suppliers, MEMs, Shippers, CDSP | 2024-11-03 | N | Preliminary Change Report published | 2024-04-25 | Preliminary Assessment | Consultation Issued | 2024-05-10 |  | Y | N
R0095 | Changes to allow DNOs to reinstate disconnected MPANs | This change has been raised to allow a DNO to reinstate MPANs which have been erroneously disconnected, regardless of the Registration Status. CSS to accommodate reinstating a registration from secured inactive to secured active. | Link | Leanne Yates | Northern Powergrid | Task Force Lydia Bentley | 2023-02-17 | 2b (Cat 2 products with technical impacts) | No | Medium | 103 | Self-Governance | TBD | Electricity | DCC, DNO, iDNO, Suppliers, Switching Providers, EES, GES, |  | Y - Interest | Change has been placed "On Hold" due to R0095's conflict with the MHHS Code Freeze. However, existing work on cost-benefit case is to continue. On Hold until Post MHHS M10. | 2024-04-10 | On Hold | Code Manager to meet again internally to discuss cost benefit case for technical solution so that when Change is removed from freeze, work can begin immediately. | 2024-05-03 |  | N | Y
R0096 | CSS Message Regeneration Functionality | Since CSS Go-Live there have been incidents whereby messages have been unsuccessfully generated by CSS and therefore are not delivered to the intended recipient. When CSS does not generate a message it results in a failure of the Switching process and can cause significant complications for the intended recipient, who is required to manually intervene to re-synchronise messages This change has been raised to enable CSS to identify and regenerate messages that failed initial generation, such that the message recipient is not impacted. | Link | Michael Taylor | Code Manager | Task Force Lydia Bentley | 2023-02-16 | 2b (Cat 2 products with technical impacts) | No | Medium | 133 | Self-Governance | TBD | Electricity and Gas | CSS Provider, EES, CSS Users |  | N | Review of the scope of the change. | 2023-11-03 | Impact Assessment (Service Provider only) | Lead Analyst to meet with REC Technical Design Authority (TDA) to understand solution development activity and discussions with the Data Communications Company (DCC) to date | 2024-05-03 |  | Y | Y
R0097 | Consequential Change for CSS Smart Meter Data Retriever Appointments | This change looks to deliver a consequential change identified during R44 detailed design. It will implement a mechanism to allow for identification of SMDR appointment messages that requires an asynchronous response. This will require the introduction of an ‘acknowledgement required flag’ | Link | Michael Taylor | Code Manager | Harriet Truss | 2023-02-17 | 2b (Cat 2 products with technical impacts) | Yes | Critical | 175 | Self-Governance | Technical Expert Panel | Electricity | ERDS Providers. (CSS Provider, GRDS Provider) | MHHS M8 | Y - Conseq | Approved for implementation by Change Panel on 04/07/2023 | 2023-07-04 | Awaiting Implementation | Implementation | MHHS M8, 07/03/2025 |  | N | Y
R0098 | Optional fuzzy searching in EES | This change seeks to introduce new configuration settings in to the EES API - to enable a search to be exact or fuzzy. | Link | Andrew Dawson | GB Group Plc | Task Force Elise Handy | 2023-03-03 | 2b (Cat 2 products with technical impacts) | No | Low | 88 | Self-Governance | Technical Expert Panel | Electricity | EES Provider | 2024-06-28 | N | Final Change Report approved at Technical Expert Panel | 2024-03-27 | Awaiting Implementation | Implementation | 2024-06-28 |  | N | N
R0099 | CSS End User Obligations | There are multiple observed instances of CSS incidents that have been raised that cannot be resolved without proactive engagement from the end user. There are currently no direct obligations on CSS Users to engage with the incident resolution process, or to provide up to date contact details, which can result in the CSS System Operator struggling to resolve incidents in a timely manner. This results in CSS incidents remaining unresolved and results in a degradation of the effectiveness of the switching process. This Change Proposal has been raised to address this issue. | Link | Michael Taylor | Code Manager | Task Force Elise Handy | 2023-03-10 | 2a (Cat 2 products without technical impacts) | No | Low | 108 | Self-Governance | Change Panel | Electricity and Gas | CSS Users |  | N | Code Manager is working with the Proposer on a non-legal text solution. | 2024-04-12 | Solution Development | Code Manager to determine a suitable solution outside of a Change Proposal. | 2024-05-31 |  | N | Y
R0100 | Update to Error Handling Documents | There are duplications between the CSS Message Business Data Validation Rules document (a Category 2 document) and the CSS Error Processing guide (a Category 3 guidance document), which is resulting in confusion and complications within the error handling process. This Change Proposal has been raised to update the Business Data Validation Rules document, to capture the appropriate information that is removed from the CSS Error Processing guide and to ensure alignment with newly created knowledge articles | Link | Michael Taylor | Code Manager | Task Force Gemma Dixon | 2023-03-15 | 2b (Cat 2 products with technical impacts) | No | Low | 57 | Self-Governance | TBD | Electricity and Gas | CSS Users |  | N | Draft solution prepared. | 2023-11-07 | Solution Development | To be reviewed by St Clements prior to plan for progression of the change. | 2024-05-03 |  | Y | Y
R0105 | Review of ONAGE SLAs | In light of the changes introduced as part of the Switching Programme, it is appropriate to review the SLAs and lead times around the sending and receiving/processing the ONAGE | Link | Natalie Hitchman | SGN Metering | Task Force Lydia Bentley | 2023-04-04 | 2b (Cat 2 products with technical impacts) | No | Low | 84 | Self-Governance | Metering Expert Panel | Gas | Metering Equipment Managers, Gas Suppliers |  | N | Code Manager to present Initial Assessment Report and Change Proposal Plan to Change Panel | 2024-04-16 | Solution Development | Solution Development Acitivity to close. During Solution Development, the Code Manager will take advise from industry experts and conduct analysis to determine how, if at all, to reduce the ONAGE SLA. | 2024-05-31 |  | N | N
R0108 | Enabling Electricity Enquiry Service searches using a Unique Property Reference Number | This Change Proposal seeks to add functionality to the EES, to return meter point details for one or multiple meter points (MPANs) from a search of UPRN | Link | Andrew Dawson | GB Group Plc | Task Force Elise Handy | 2023-03-09 | 2a (Cat 2 products without technical impacts) | No | Low | 88 | Self-Governance | Technical Expert Panel | Electricity | TPIs, Suppliers | 2024-08-23 | N | Final Change Report approved at Technical Expert Panel | 2024-03-27 | Awaiting Implementation | Implementation | 2024-08-23 |  | N | N
R0113 | Data Specification Housekeeping and Clarifications | At present, there are several gaps or misaligned references not transferred into the present REC Data Specification which causes confusion for parties, especially new entrants. There is a risk that the ambiguities in the Data Specification could make it challenging for parties to follow the Data Specification and result in Market Messages being sent that do not correctly reflect the rules of the Data Specification. This may result in Market Message rejections, which may in turn have impacts for Consumers and other Market Participants This change seeks to update relevant legal text in the REC (Retail Energy Code) Data Specification to provide clarification and alignment from previous legacy documents to parties. This will ensure existing parties have a consistent understanding and new entrants are able to set up their systems as appropriate. | Link | April Harbour | Code Manager | Task Force Gemma Dixon | 2023-04-18 | 1a (Cat 1 products without technical impacts) | No | Low | 57 | Self-Governance | TBD | Electricity and Gas | All REC Parties |  | N | Consolidated impact assessment period with the Code Manager commenced. | 2024-04-25 | Solution Development | Consolidated Impact Assessment period close. | 2024-05-10 |  | N | N
R0115 | Frequency and content of CSS reports on switching via the DCC portal | This change has been raised by Ofgem to make updates to CSS reports provided by the Switching Operator; for these be provided on a weekly basis and be designed in such a way that genuine switches between Suppliers are reported. At present the latter is not possible as all switches at MPID level are reported with no indication of switching flows. | Link | Monica Gandolfi | Ofgem | Task Force Elise Handy | 2023-04-19 | 2b (Cat 2 products with technical impacts) | No | Medium | 128 | Authority-Approval | TBD | Electricity and Gas | No impacted Parties, DCC as Service Provider. |  | N | Authority decision received to approve R0115 | 2024-04-23 | Awaiting Implementation |  |  |  | N | Y
R0116 | TPI access to the Meter Asset Manager data via the GES | TPIs do not currently have access to the MAM via GES. Provision of the MAM will allow TPIs to identify and contact the relevant MAM to arrange direct MAM agreements for clients on their behalf. | Link | Chris Felgate | Ginger Energy | Task Force Elise Handy | 2023-04-19 | 1b (Cat 1 products with technical impacts) | No | Low | 86 | Self-Governance | TBD | Gas | Third Party Intermediaries |  | N | Service Provider Impact Assessment received. | 2023-12-06 | Solution Development | Consideration of different technical solution. To be taken down the R0118 route. | 2024-05-19 |  | Y | N
R0119 | Annulment Definition | The performance assurance team have identified Parties using annulments when they should use other processes. The lack of a clear definition of what an annulment is could be a contributing factor to this. | Link | Anton Moden | Code Manager | Task Force James Hardy | 2023-05-16 | 1a (Cat 1 products without technical impacts) | No | Low | 97 | Authority-Approval | TBD | Electricity and Gas | All REC Parties |  | N | Consolidated impact assessment period | 2024-02-16 | Initial Assessment | Initial Assessment Report and Change Proposal Plan | 2024-05-09 |  | N | N
R0120 | Ability to search GES API using Meter Serial Number | This change seeks to enable searches of GES API by Meter Serial Number, which is enough information to enable the return of all meter-point data associated with the MPRN. | Link | Andrew Dawson | GB Group Plc | Task Force Elise Handy | 2023-05-10 | 2b (Cat 2 products with technical impacts) | No | Low | 62 | Self-Governance | TBD | Gas | Suppliers and Third Party Intermediaries, MEMs, MAPs. |  | N | Preliminary Impact Assessment received from Service Provider. | 2024-04-25 | Impact Assessment (Service Provider only) | Detailed Impact Assessment to be sent to Service provider. | 2024-05-10 |  | Y | N
R0121 | SDEP Review Improvements (1) - Process Types | This change will improve (Process Types and escalations) operational efficiency for users of the SDEP system, which offers opportunities for REC Parties to enhance how consumer-related queries are dealt with (time and accuracy). | Link | Ryan Dale | Code Manager | Task Force Elise Handy | 2023-05-26 | 1b (Cat 1 products with technical impacts) | No | High | 169 | Self-Governance | Technical Expert Panel | Electricity and Gas | Energy Suppliers, DNOs | 2024-08-23 | Y - Interest | Technical Expert Panel approved R0121 for implementation 23/08/2024. | 2024-04-24 | Awaiting Implementation |  | 2024-08-23 |  | N | N
R0122 | SDEP Review Improvements (2) - Usability | This change will improve (Usability) operational efficiency for users of the SDEP system, thereby allowing consumer issues to be addressed sooner / more accurately. | Link | Ryan Dale | Code Manager | Task Force Elise Handy | 2023-05-26 | 2b (Cat 2 products with technical impacts) | No | Medium | 126 | Self-Governance | TBD | Electricity and Gas | Energy Suppliers, DNOs |  | N | Special REC Issues Group to discuss. | 2023-10-20 | On Hold |  |  |  | N | N
R0123 | SDEP Review Improvements (3) - Look and feel | This change will improve (Look and Feel) operational efficiency for users of the SDEP system and therefore give more opportunity for timely rectification of consumer issues. | Link | Ryan Dale | Code Manager | Task Force Elise Handy | 2023-05-26 | 2b (Cat 2 products with technical impacts) | No | Medium | 103 | Self-Governance | TBD | Electricity and Gas | Energy Suppliers, DNOs |  | N | Special REC Issues Group to discuss. | 2023-10-20 | On Hold |  |  |  | N | N
R0124 | SDEP Review Improvements (4) - Reporting | This change will improve (Reporting) operational efficiency for users of the SDEP system | Link | Ryan Dale | Code Manager | Task Force Elise Handy | 2023-05-26 | 2b (Cat 2 products with technical impacts) | No | Medium | 103 | Self-Governance | TBD | Electricity and Gas | Energy Suppliers, DNOs |  | N | Special REC Issues Group to discuss. | 2023-10-20 | On Hold |  |  |  | N | N
R0125 | SDEP Review Improvements (5) – multilateral Erroneous Switches | This change will improve (multilateral Erroneous Switches) operational efficiency for users of the SDEP system | Link | Ryan Dale | Code Manager | Task Force Elise Handy | 2023-05-26 | 2b (Cat 2 products with technical impacts) | No | Medium | 103 | Self-Governance | TBD | Electricity and Gas | Energy Suppliers, DNOs |  | N | Request for Information closure | 2024-02-16 | Solution Development | Code Manager to review RFI responses and plan next actions | 2024-05-01 |  | N | N
R0126 | SDEP Review Improvements (6) – SDEP User Guide and Obligations | This change will improve (SDEP User Guide and Obligations) operational efficiency for users of the SDEP system | Link | Ryan Dale | Code Manager | Task Force Elise Handy | 2023-05-26 | 2b (Cat 2 products with technical impacts) | No | Low | 71 | Self-Governance | TBD | Electricity and Gas | Energy Suppliers, DNOs |  | N | Solution development and stakeholder engagement underway. | 2023-07-27 | Solution Development | Refine requirements. | 2024-05-01 |  | N | N
R0130 | Updates to the Data Access Matrix | There are organisations that are named in Schedule 12 - Data Access that are not recorded in the gas and/or electricity Data Access Matrix (DAM). This means it is not possible for the Code Manager to provision them access. All organisations listed in Schedule 12 to access data in the REC should have an entry in the Data Access Matrices. This Change Proposal has been raised to review the Schedule and DAMs and take forward the necessary changes. | Link | Anton Moden | Code Manager | Task Force Elise Handy | 2023-05-30 | 2b (Cat 2 products with technical impacts) | No | Low | 59 | Self-Governance | TBD | Electricity and Gas | EES & GES Provider |  | N | Lead Analyst assigned. This change is currently being looked at alongside all REC access requests. | 2023-05-30 | Solution Development | To be taken through R0118 route. Access approved through PAB, awaiting technical implementation. | 2024-05-01 |  | Y | N
R0131 | Creation of new Enquiry Service User Category | This change has been raised to introduce a new User Category in to the Data Access Schedule, for organisations offering services that provide insight on CO2 emissions and energy consumption, to support reporting for regulatory and certifications purposes. | Link | Tony Sarkis | Deepki | Task Force Elise Handy | 2023-05-30 | 2b (Cat 2 products with technical impacts) | No | Low | 62 | Self-Governance | TBD | Gas | No impacted parties |  | N | Change Proposal Raised | 2023-05-30 | Initial Assessment | To be taken through R0118 route. | 2024-05-01 |  | TBD | N
R0137 | Introducing Third Party Intermediary (energy broker) assurance and accreditation | Introducing Third Party Intermediary (energy broker) assurance and accreditation | Link | Jon Dixon | RECCo | Caroline Freimuller | 2023-07-20 | 2a (Cat 2 products without technical impacts) | No | Critical | 183 | Authority-Approval | Change Panel | Electricity and Gas | Suppliers, TPIs, Code Manager |  | N | Asked RECCo for update when solution is due to be received | 2024-04-04 | Initial Assessment | Waiting to receive solution detail from RECCo | 2024-04-05 | FALSE | N | N
R0142 | Amendment to Multiplication Factor Enumerations to support hydrogen trials | If the enumerations of the Multiplication Factor are not amended then any consumer in the Hydrogen Trials would be disadvantaged in that they would be charged more for the energy that they are consuming. | Link | David Addison | Xoserve | Lydia Bentley | 2023-06-23 | 2b (Cat 2 products with technical impacts) | Yes | Medium | 138 | Self-Governance | Technical Expert Panel | Gas | Gas Consumers, GTs, CDSP, Gas Suppliers, MEMs |  | N | Final Change report presented at Technical Expert Panel and approved for Implementation | 2024-02-28 | Awaiting Implementation | Awaiting Implementation | 2024-06-28 |  | Y | Y
R0144 | Allowing different Metering Equipment Managers (MEMs) to be appointed to Import and Export Metering Points | Cross-code Change relating to BSC P459, relating to management of Import and Export MEMs | Link | Colette Baldwin | Code Manager | Caroline Freimuller | 2023-08-17 | 1a (Cat 1 products without technical impacts) | No | High | 157 | Authority-Approval | Metering Expert Panel | Electricity | Suppliers/MEMs/DNOs/EES |  | Y - Interest | Initial Assessment Report and Change Proposal Plan approved. | 2024-04-16 | Solution Development | Solution development | 2024-06-30 |  | N | Y
R0146 | Data Specification Update for Refresh Functionality | The Data Specification will require updating to bring it in line with the technical changes that will be implemented as part of Change Proposal R0067. | Link | Michael Taylor | Code Manager | Task Force Elise Handy | 2023-08-18 | 2a (Cat 2 products without technical impacts) | No | Low | 93 | Self-Governance | Technical Expert Panel | Gas | GRDA, CSS | 2024-06-28 | N | Change Proposal Raised | 2023-08-18 | Solution Development | Initial Assessment in progress. Change Plan to be presented to Change Panel | 2024-05-07 |  | Y | Y
R0148 | Introduction of classification-based access model into the REC in support of Open Data | This change proposal is seeking to improve, extend and simplify access to enquiry services’ data securely and efficiently. Currently enquiry services’ data is only available to users whose roles and purpose for access are detailed in schedule 12 of the REC. RECCo have undertaken a project (Open Data project referenced in the 23/24 FWP) to look at REC controlled data sources and create a metadata catalogue based on a data classification model. This details the data items along with descriptions, identification of the associated data roles & responsibilities and classification. RECCo are proposing that the output of this work is utilised to extend and improve access to Enquiry Services’ data. This will be achieved through broader and more tailored access to Enquiry Services data which is available, by making certain data items (defined as ‘Always Open’) easily available to anyone, and simplifying the approval process for those data items which can be made available so long as certain conditions have been met (tailored access). No existing access to data will be reduced for users currently accessing the enquiry services. | Link | Tracy Hardy | RECCo | Task Force Elise Handy | 2023-10-13 | 1b (Cat 1 products with technical impacts) | No | High | 170 | Self-Governance | Change Panel | Electricity and Gas | All Enquiry Service Users |  | Y - Interest | Impact Assessment of metadata catalogue closed. | 2024-01-26 | Solution Development | Review of comments and propose any changes to categorisation. | 2024-05-03 |  | Y | N
R0150 | On-site Aggregation as a method to facilitate Third Party Access - BSC P455 | Customers on private networks may be supplied electricity from the Boundary Point Supplier. The Boundary Point Supplier is usually appointed by the Private Network Operator (PNO). Customers on private networks also have the right to switch to a Third Party Supplier (TPS) of their choice. Under the Electricity and Gas (Internal Markets) Regulations 2011 (Statutory Instrument (SI) 2011 No. 2704), PNOs are obligated to facilitate access to TPSs. Where one or more customers on a PNO for a third party supply, corrective action is required to avoid the double counting of metered volumes in Settlement. This is because Third Party Meter readings submitted into Settlement by the TPS Agent also contribute to the aggregate Boundary Point Meter reading submitted into Settlement and allocated to the energy account of the Boundary Point Supplier. The BSC Change indicates that they see inefficiencies aris in the differencing metering approach when there is more than one TPS supplying customers on a private network. For example, where a private network is connected to 100 domestic properties, 50 of which are supplied by a license exempt Supplier appointed by the PNO and 50 of which are supplied by 20 different TPSs, all 20 TPSs must establish the bespoke arrangements mentioned above to facilitate the scheme. | Link | Colette Baldwin | Code Manager | James Hardy | 03/10/2023 | 1b (Cat 1 products with technical impacts) | No | Medium | 133 | Self-Governance | Metering Expert Panel | Electricity | MEMs | 2024-06-28 | Y - Interest | Final Change Report Published | 2024-04-25 | Final Assessment | Final Change Report to be voted on by Responsible Committee | 2024-05-08 |  | N | N
R0152 | Revision to the Consolidated Metering Code of Practice (CoMCoP) | The new consolidated Metering Code of Practice was implemented on 01 April 2023. Since its implementation a number of issues have been identified and some have been raised to RECCo and the Code Manager by REC Parties where they are unable to meet their obligations. The Code Manager has reviewed these and determined changes are required. | Link | Tina Pearce | Code Manager | Caroline Freimuller | 2023-11-03 | 1a (Cat 1 products without technical impacts) | No | Medium | 113 | Self-Governance | Change Panel | Electricty and Gas | MEMS, Suppliers & DNOs |  | N | Solution Development Phase 1 (ensuring clauses are assigned to the correct Parties) complete | 2024-03-04 | Solution Development | Work groups in place weekly until the end of July | 2024-07-31 |  | N | N
R0153 | Catering for Registration Events | In some instances, the incumbent Supplier is withdrawing prior to the ‘Supply Effective from Date’ which causes the accepted Switch to fail at Gate Closure (17:00hrs) | Link | David Addison | Xoserve | James Hardy | 2023-10-31 | 1b (Cat 1 products with technical impacts) | No | Low | 95 | Self-Governance | Change Panel | Electricity and Gas | Switching Data Service Providers, Central Switching Service Provider Suppliers |  | TBD | Technical workshop series to discuss changes needed under CP and actions required. | 2024-01-20 | Solution Development | Action with Service Provider/RTS to determine whether or not the issues identified with the CSS Business Process Logic are to be classified as defects in the system. DCC to internally review the issues that have been identified by Landmark and provide their position on how these should be resolved | 2024-04-02 | FALSE | TBD | Y
R0155 | Change of Tenancy: Evidentiary Standards and Timescales | Non-domestic energy contracts commit the consumer to a fixed duration and unlike domestic consumers, they are less able to change supplier mid-term. However, there are instances where a non-domestic premises undergoes a Change of Tenancy (CoT), and the incoming tenant/owner who inherits the supply point and its relationship to the predecessors chosen energy supplier may wish to make alternative arrangements that best matches their needs. In these circumstances, the incoming tenant may choose to enter a new contract with the same supplier or take up a wholly new contract with a new supplier. | Link | Suchitra Hammond | RECCo | James Hardy | 2023-12-13 | 1b (Cat 1 products with technical impacts) | Yes | Medium | 133 | Authority-Approval | Change Panel | Electricity and Gas | Suppliers |  | N | CPP Extension approved at Change Panel | 2024-04-16 | Solution Development | Solution Development Working Group | 2024-06-28 |  | Y | Y
R0157 | Removal of Facsimile as a method of Code Communication | The Public Switched Telephone Networks (PSTN) will be switched off in December 2025 by all telecom companies and will be replaced with an Internet Protocol (IP) digital network. | Link | Colette Baldwin | Code Manager | James Hardy | 2023-12-12 | 1b (Cat 1 products with technical impacts) | No | Medium | 118 | Self-Governance | Change Panel | Gas and Electricity | Suppliers, MEMS, Green Deal Providers, Green Deal Finance Providers, Data Collectors | 2025-11-01 | N | Final Change Report Approved by the Change Panel | 2024-03-19 | Awaiting Implementation | Awaiting Implementation. Release date update to be provided in due course. | 2025-11-01 |  | Y | N
R0158 | Amendment to the ‘Supplier Registration Report (MAP)’ report methodology | Register (highlighted). Following a query into the report methodology initiated by the CDSP as part of their reporting checks it was identified that reports were being issued to MAPs that contained Supply Meter Points that did not have the requesting MAP recorded in the UK Link system as the MAP for that Supply Meter Point. | Link | David Addison | Xoserve | Lydia Bentley | 2023-11-30 | 1b (Cat 1 products with technical impacts) | No | Low | 88 | Self-Governance | Technical Expert Panel | Gas | Gas Consumers, Domestic Prepayment, Domestic Credit, Microbuisness, Small and Medium Enterprise (SME) and Industrial and Commercial (I&C) | 2024-06-28 | N | Change Approved by the Rechnical Expert Panel | 2024-04-24 | Awaiting Implementation | Implementation | 2024-06-28 |  | N | N
R0160 | Electricity Supply to Hydrogen Electrolysers | Primary legislation for hydrogen production does not mention the role of Licensed Suppliers. Consequently, the LCCC does not have the power needed to compel Licensed Suppliers to disclose the information needed by the LCCC to carry out its duties with regards the Hydrogen Production Business Model (HPBM) and Low Carbon Hydrogen Agreement (LCHA) to prove that the electricity is compliant with the Low Carbon Hydrogen Standard (LCHS) . | Link | Brett Ryan | Hydrogen Uk | James Hardy | 2024-03-15 | 1a (Cat 1 products without technical impacts) | No | High | 165 | Authority-Approval | Change Panel | Electricity | Electricity Suppliers | 2024-06-28 | N | Preliminary Change Report published for Consultation | 2024-04-25 | Consultation | Consultation to close. | 2024-05-21 |  | N | N
R0161 | Enabling Robotics for SDEP | The Secure Data Exchange Portal (SDEP) is a mailbox that enables the transfer of sensitive customer related data in a way that ensures data is safe and secure. Suppliers are obliged to send and receive queries and escalations via the SDEP. Unfortunately, the SDEP has issues in bulk resolving processes which could be solved by the removal of the prohibition of the use of robotics. For example, there is no function to be able to retrieve cases specific to each team, work these and then automatically issue a response. Currently, to get the same kind of functionality, an agent or team lead would need to manually process. In another scenario, under REC schedule 30, as part of each of the processes, we are obliged to issue an escalation where there has been no response within set timeframes. Prior to SDEP implementation, we would be able to issue email escalations automatically where there was an absence of a response flow. With the SDEP this process is now manual: an agent will need to sign in to ECOES, navigate to the appropriate module, and input the data. | Link | David Morley | Ovo | Gemma Dixon | 2024-03-08 | 1a (Cat 1 products without technical impacts) | No | Low | 75 | Self -Governance | Technical Expert Panel | Gas and Electricity | Energy Suppliers |  | N | New Change Proposal Accepted | 2024-03-27 | On Hold | On Hold until Post MHHS M10 | Post MHHS M10 |  | TBD | N
R0162 | Access to SDES for Gas Networks | Raising on behalf of the Gas Networks, who currently struggle to find who to email queries to within suppliers organisation. Suppliers and Electricity DNO's moved to SDES to ensure all communications were in a secure portal, with SLA's and for GDPR reasons, but Gas Networks do not have access to this portal, and not considered during the implementation of the system. They also obtain photo's when out on site to help resolve queries and would like somewhere to upload them to send to suppliers. | Link | Angela Joyce | Octopus | Caroline Freimuller | 2024-02-29 | TBD | No | Low | 100 | Self -Governance | TBD | Gas | Gas Networks |  | N | New Change Proposal Accepted | 2024-03-27 | On Hold | On Hold until Post MHHS M10 | Post MHHS M10 |  | TBD | TBD
R0163 | Theft Detection Incentive Scheme (TDIS) Reporting Periods | Theft of energy significantly increases the cost to bill-paying consumers and poses serious risk to people and property. Gas and Electricity Suppliers have obligation under the standard conditions of their licence to prevent, detect and investigate theft. However, even where theft is detected and proven, there is no certainty that the Supplier will be able to recover any money from the consumer. The Theft Detection Incentive Scheme (TDIS) is therefore intended to offset the costs to suppliers of undertaking such activities. Under the scheme, each Energy Supplier is allocated a proportion of an overall Theft Target, proportionate to their share of both the domestic and non-domestic sectors of the market in both gas and electricity. Those Energy Suppliers who outperform their competitors will receive an incentive payment, while those who underperform will be net contributors. While the Theft Targets may be subject to evidence-based revisions, the aggregate targets have in practice not been substantively altered since the scheme was introduced. Feedback received from a number of stakeholders including the Energy Theft Reduction Expert Group and wider REC Parties, for instance through consultation on the Theft Target Methodology, suggest that there is growing concern at both the performance of individual Energy Suppliers, and of the overall efficacy of the scheme in reducing levels of theft. In November 2023 Ofgem wrote to all Energy Suppliers setting out its initial observations on suppliers’ performance in relation to their licence and code obligations. For instance, Ofgem noted that the overall performance of Energy Suppliers had fallen short of TDIS targets over the past two years, with confirmed thefts being around 40% of the aggregate Theft Target. There may be a number of factors affecting the achievement against targets, including the appropriateness of the prevailing targets themselves. However, the current design of the scheme including the annual reporting cycle limits the opportunities to make appropriate adjustments. | Link | Jon Dixon | RECCo | Elise Handy | 2024-02-28 | 1a (Cat 1 products without technical impacts) | No | Medium | 135 | Self -Governance | Change Panel | Gas and Electricity | Energy Suppliers, Code Manager | 2024-06-28 | N | Preliminary Change Report and Consultation published | 2024-04-12 | Consultation | Consultation to close | 2024-05-03 |  | N | N
R0164 | Removing the Enumerations from Communications Method Data Item (J0386) to align with BSC CP 1594 | BSC has raised Change Proposal CP1594 which seeks to create an approvals process and a valid set for communications method. This change is proposing to create an approvals process to allow for the managed end dating of older technologies, such as Public switched telephone network (PSTN), Circuit Switched Data (CSD) and later 2G, and the assessment of the validity of newer communications technologies, such as (but not exclusively) Narrow Band-Intern of Things (NBIoT) and Category M (CAT-M). The evolution of metering communication systems underscores the need for timely updates. Legacy systems risk inefficiencies and potential security vulnerabilities. Implementing an approval process, modelled on BSCP601, ensures a standardised approach to introducing new technologies and managing the exit of old ones. Further justifications include: • To allow for the centrally managed end-dating of redundant communications technologies in line with known deadlines for those technologies to become redundant and unreliable. • To allow for the wider industry education of newer types of communication technologies. • To create and expand the already existing central knowledge base of the evolution and attributes of newer communication technologies as they relate to Settlement Metering Equipment. • To ensure transparency for all industry participants on the newer communications types available and the dates for which legacy communications must be removed. CP1594 will create a valid set, linked to the new approval process and using Data Item J0386 as a conduit to detail the approved communication methods as well as end dates for communication methods which are becoming redundant and unreliable. | Link | Christopher Day | Elexon | Lydia Bentley | 2024-04-09 | TBD | No | Medium | 135 | Self-Governance | Change Panel | Electricity | Suppliers, DNOs, MEMs |  | TBD | Initial Assesment Report and Change Proposal Plan approved ex-committee 24/04/24. | 2024-04-24 | Party Impact Assessment | Publish Preliminary Change Report and Consultation | 2024-05-23 |  | N | N
R0165 | Prepayment Method Levelisation Reconciliation Housekeeping Change | The Code Manager has identified typographical and formatting errors, as well as opportunities to provide clarity, improve consistency and accuracy across the REC Services and products. These changes have been assessed as meeting the criteria to be progressed via a Housekeeping Change Proposal. Schedule 31 - Prepayment Method Levelisation Reconciliation: The Electricity and Gas Meter Point Portfolio Example's have typographical and formatting errors. | Link | Holly Law | Code Manager | Holly Law | 2024-04-16 | 1a (Cat 1 products without technical impacts) | No | Low | N/A | Self-Governance | Change Panel | Gas and Electricity | Energy Suppliers | N/A | N | Housekeepinf change report published | 2024-04-25 | Final Assessment | Change Panel | 2024-05-07 |  | N | N
R0166 | Removal of the Green Deal Panel | This Change Proposal seeks to remove the Green Deal Panel Terms of Reference from the REC Baseline Statement and product set, and to amend the Change Panel Terms of Reference to incorporate consideration of Green Deal business. | Link | Paul Rocke | Code Manager | Gemma Dixon | 2024-04-22 | 2a (Cat 2 products without technical impacts) | No | Low | 35 | Self-Governance | Change Panel | Electricity | Energy Suppliers, DNOs |  | N | Change Accepted | 2024-04-22 | Initial Assessment | Consultation Published | 2024-05-09
Note on W7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MHHS M8
Note on M35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is dependent on solution. Current proposal would be Authority, RPS has provided an alternative that would be SG.

## Portfolio View
REC CHANGE PORTFOLIO Last updated: 26/04/2024
Priority Status and Score |  | INITIAL ASSESSMENT | ON HOLD | SOLUTION DEVELOPMENT | IMPACT ASSESSMENT | PRELIMINARY ASSESSMENT | CONSULTATION | FINAL ASSESSSMENT | AWAITING AUTHORITY DETERMINATION | AWAITING IMPLEMENTATION
CRITICAL | 171
|  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HIGH | 151 170
|  | 0 | 0 | 2 | 0 | 0 | 1 | 2 | 0
MEDIUM | 101 150
|  | 0 | 7 | 3 | 3 | 1 | 1 | 1 | 0
LOW | 0 100
|  | 8 | 1 | 10 | 1 | 0 | 1 | 3 | 0
TBD
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9 | 8 | 15 | 4 | 1 | 3 | 6 | 0
R37
R06
R43
R44
R64
R70
R48
R49
R53
R157
R56
R72
R76
R60
R69
Key
On track
Progress at risk
Behind Plan
RXX
RXX
RXX
R83
R87
R80
R94
R98
R99
R105
R108
R113
R97
R115
R119
R120
R121
R122
R123
R125
R124
R126
R92
R95
R96
R100
R116
MHHS Programme Milestone: M8 ‘Code changes delivered
R130
R131
R137
R142
R144
R146
R148
R152
R150
R153
R155
28 June 2024
R92A
R158
November 2025
23 August 2024
R161
R162
R163
R160
08 November 2024
R165
R164
R166

## Implemented
Last updated: 26/04/2024
Change Proposal Reference | Change Proposal Title | Link to CP page | Proposer Name | Proposer Company | Lead Analyst | Date Submitted | Change Category | Urgent (Y/N) | Priority Status | Priority Score | Change Path | Responsible Committee | Fuel | Impacted Parties | Implementation Date
R0001 | Amendment to DCC Service Flag (DI51130) Data Item | Link | Jonathan Hawkins | Code Manager | Jonathan Hawkins | 2021-09-01 | 2b (Cat 2 products with technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | n/a | Energy Suppliers, Distribution Network Operators, Electricity Enquiry Service (ESS) Users, MPAS Providers | 2021-11-04
R0002 | Review of Data Specification Category in REC Baseline Statement | Link | Jonathan Hawkins | Code Manager | Jonathan Hawkins | 2021-09-01 | 2a (Cat 2 products without technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | n/a | Energy Suppliers, Distribution Network Operators | 2021-11-04
R0003 | Market-wide Half-Hourly Settlement Implementation | Link | Abid Sheikh | Ofgem | Jonathan Hawkins | 2021-09-01 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Authority-Approval | Change Panel | n/a | Suppliers, Network Parties, and the DCC | 2021-11-04
R0008 | Consequential New and Amended Market Messages for BSC Modification P375 | Link | Colin Berry | Elexon | Gemma Dixon | 2021-09-08 | 2b (Cat 2 products with technical impacts) |  | n/a | n/a | Self-Governance | Technical Expert Panel | Electricity | Energy Suppliers, Distribution Network Operators | 2022-06-30
R0010 | New Meter Types for AuxilInitial Assessment Reporty Proportional Controllers (APCs) | Link | David Morton | EDF | Jonathan Holland | 2021-09-08 | 1b (Cat 1 products with technical impacts) |  | Low | n/a | Self-Governance | Technical Expert Panel | Electricity | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers, DCC, Data Collectors, EES Users, Prepayment Meter Infrastructure Provider, Meter Point Administration Service | 2023-06-30
R0011 | Reporting of additional EMR Backing Data to Suppliers | Link | Ben Lathbury | EMRS | Gemma Dixon | 2021-09-08 | 1b (Cat 1 products with technical impacts) |  | Low | n/a | Self-Governance | Technical Expert Panel | Electricity | Energy Suppliers | 2023-06-30
R0012 | Housekeeping amendments to REC V2 | Link | Jonathan Hawkins | Code Manager | Jonathan Hawkins | 2021-10-04 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | n/a | No impacted parties | 2022-01-31
R0014 | Cable Colour Identification | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2021-11-01 | 2a (Cat 2 products without technical impacts) |  | n/a | n/a | Self-Governance | Metering Expert Panel | n/a | Metering Equipment Managers | 2022-06-30
R0015 | Remote communication obligations for electricity Advanced Meters | Link | David Brown (originally Tom Chevalier) | Association of Meter Operators | Harriet Truss | 2021-11-17 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Authority-Approval | Change Panel | Electricity | Energy Suppliers, Metering Equipment Managers, Data Collectors | 2023-06-30
R0017 | Invalid Requests for Site Technical Details | Link | Elaine Carr | Scottish Power Energy Networks | Ann Perry | 2021-11-22 | 1b (Cat 1 products with technical impacts) |  | Low | 91 | Self-Governance | Metering Expert Panel | Electricity | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers | 2023-11-03
R0018 | Complex Sites process improvements | Link | Ann Perry | Code Manager | Jonathan Holland | 2021-11-25 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Self-Governance | Metering Expert Panel | n/a | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers | 2022-11-04
R0019 | Consequential REC Changes for BSC CP1532 | Link | Ann Perry | Code Manager | Ann Perry | 2021-11-26 | 1b (Cat 1 products with technical impacts) |  | n/a | n/a | Self-Governance | Metering Expert Panel | n/a | Energy Suppliers and Metering Equipment Managers | 2022-06-30
R0020 | ETTOS Report Dissemination | Link | Aiyesha Andrade | RECCo | Ann Perry | 2021-11-29 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | n/a | n/a | 2022-01-31
R0021 | Allowing REC accredited MEMs to de-energise and re-energise supply points independent of the Supplier | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2021-12-09 | 2b (Cat 2 products with technical impacts) |  | n/a | n/a | Authority-Approval | Metering Expert Panel | Electricity | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers | 2023-06-30
R0022 | Amendment to REC Data Access Matrix | Link | Harriet Truss | Code Manager | Harriet Truss | 2021-12-15 | 1b (Cat 1 products with technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | Electricity and Gas | EES Users | 2022-11-04
R0023 | Prepayment Unallocated Transactions | Link | Jonathan Holland | Code Manager | Jonathan Holland | 2021-12-15 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | n/a | The Code Manager | 2022-06-30
R0025 | Service Provider Performance Charges (DCC) | Link | Eliana Campbell | Code Manager | Gemma Dixon | 2022-01-04 | 1a (Cat 1 products without technical impacts) |  | Medium | 118 | Authority-Approval | Performance Assurance Board | n/a | DCC | 2023-04-01
R0028 | Review of Category 3 documents in the REC Baseline Statement | Link | Anton Moden | Code Manager | Gemma Dixon | 2022-01-07 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | n/a | n/a | 2022-04-14
R0030 | Erroneous Transfer Cancellations | Link | Lorna Mallon | Scottish Power Energy Retail | Gemma Dixon | 2022-01-14 | 1b (Cat 1 products with technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | Electricity and Gas | Energy Suppliers | 2023-06-30
R0031 | Altering the Trigger Points for CT Commissioning | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2022-01-26 | 2b (Cat 2 products with technical impacts) |  | n/a | n/a | Self-Governance | Metering Expert Panel | n/a | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers | 2022-11-04
R0032 | New Registration data items and processes to support the transition to Market-wide Half-Hourly Settlement (MHHS) | Link | Colette Baldwin | Code Manager | Gemma Dixon | 2022-02-03 | 1b (Cat 1 products with technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | Electricity | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers, EES Users | 2023-06-30
R0033 | Micro-business Smart Meter Installation Reports | Link | Kelly Austin | EDF | Colette Baldwin | 2022-01-31 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | n/a | Energy Suppliers | 2022-11-04
R0034 | Market Stabilisation Charge | Link | Henry Kemp | Ofgem | Ann Perry | 2022-02-17 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Authority-Approval | Change Panel | n/a | n/a | 2022-04-14
R0035 | Market Stabilisation Charge - Administration | Link | Jon Dixon | RECCo | Ann Perry | 2022-02-21 | 1b (Cat 1 products with technical impacts) |  | n/a | n/a | Authority-Approval | Change Panel | n/a | n/a | 2022-06-30
R0036 | Extensive Housekeeping amendments | Link | Ann Perry | Code Manager | Jonathan Holland | 2022-03-04 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | n/a | Energy Suppliers, Distribution Network Operators, Gas Transporters, Metering Equipment Managers, DCC, Shippers, Data Collectors, Data Aggregators, Green Deal Providers, Green Deal Finance Parties, Meter Asset Providers, AMR Service Providers, EES Users, GES Users, GDCC Users | 2022-11-04
R0038 | Performance Assurance Report Catalogue Changes as a consequence of REC V3.0 | Link | Lewis Williams | Code Manager | Gemma Dixon | 2022-03-23 | 2a (Cat 2 products without technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | n/a | n/a | 2022-07-18
R0039 | Revised Implementation Date for R0011 | Link | Patrick Bibby | LCCC | Gemma Dixon | 2022-03-25 | 2b (Cat 2 products with technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | n/a | Energy Suppliers, Generators and Capacity Providers | 2022-06-01
R0041 | REC V3.0 | Link | Alasdair MacMillan | Ofgem | Ann Perry | 2022-04-07 | 1b (Cat 1 products with technical impacts) |  | n/a | n/a | Authority-Approval | Change Panel | n/a | n/a | 2022-07-18
R0042 | Performance Assurance Board Terms of Reference | Link | Eliana Campbell | Code Manager | Jonathan Holland | 2022-04-14 | 2a (Cat 2 products without technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | n/a | n/a | 2022-07-18
R0045 | Changes to SDEP Messages and Schedule numbering for REC V3 | Link | Jon Hawkins | RECCo | Gemma Dixon | 2022-05-04 | 2a (Cat 2 products without technical impacts) |  | n/a | n/a | Self-Governance | Technical Expert Panel | n/a | No impacted parties | 2022-07-18
R0046A | Governance of Data under the REC (Alternative) | Link | Brian O'Shea | RECCo | Jonathan Holland | 2022-05-20 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Authority-Approval | Change Panel | n/a | Energy Suppliers, Gas Transporters, DNOs, Metering Equipment Managers, Non-REC party service users and the DCC | 2022-08-03
R0047 | Metering Code of Practice Consolidation Review | Link | Aiyesha Andrade | RECCo | Ann Perry | 2022-05-20 | 1a (Cat 1 products without technical impacts) |  | n/a | n/a | Self-Governance | Change Panel | Electricity and Gas | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers | 2023-04-01
R0052 | GES Service Definition Document | Link | Cristina Bermudez Alvarez | Code Manager | Elise Handy | 2022-06-13 | 2a (Cat 2 products without technical impacts) |  | Low | 57 | Self-Governance | Technical Expert Panel | Gas | GES Provider, Metering Equipment Managers, Meter Asset Providers | 2023-02-24
R0054 | EES Access for Virtual Lead Parties | Link | Ann Perry | Code Manager | George Barnes | 2022-06-17 | 2b (Cat 2 products with technical impacts) |  | Low | n/a | Self-Governance | Technical Expert Panel | Electricity | EES Provider, Virtual Lead Parties | 2023-04-01
R0055 | Switching Operator Outage Notification Lead time | Link | Cordelia Grey | DCC | Ann Perry | 2022-07-06 | 2a (Cat 2 products without technical impacts) |  | n/a | n/a | Self-Governance | Technical Expert Panel | Electricity and Gas | DCC, GRDS Provider, ERDS Providers, EES Provider, GES Provider | 2023-02-24
R0059 | Maintenance of Qualification Schedule Change | Link | Georgina Scott-Picton | Code Manager | Jonathan Holland | 2022-08-05 | 1a (Cat 1 products without technical impacts) |  | Low | 61 | Self-Governance | Performance Assurance Board | Electricity and Gas | All REC Service Users | 2023-11-03
R0066 | Inclusion of SMRS Data Items in EES (BSC CP1568 Consequential Change) | Link | Gemma Dixon | Code Manager | Gemma Dixon | 2022-08-26 | 1b (Cat 1 products with technical impacts) |  | Low | 108 | Self-Governance | Change Panel | Electricity | EES Users | 2023-06-30
R0067 | Introduction of CSS refresh functionality | Link | Michael Taylor | Code Manager | Elise Handy | 2022-08-26 | 2b (Cat 2 products with technical impacts) |  | Low | 109 | Self-Governance | Technical Expert Panel | Gas | CSS Provider, Switching Data Service Providers, Energy Suppliers, EES | 2023-12-06
R0071 | DCC access to EES and GES | Link | Cordelia Grey | DCC | Lydia Bentley | 2022-09-12 | 1a (Cat 1 products without technical impacts) |  | Medium | 123 | Self-Governance | Change Panel | Electricity and Gas | Switching Service Desk, EES Provider, GES Provider | 2024-02-23
R0073 | Housekeeping Change Process | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2022-09-27 | 1a (Cat 1 products without technical impacts) |  | Low | 76 | Self-Governance | Change Panel | n/a | Code Manager, REC Parties and Service Providers | 2023-04-01
R0074 | Release of Community View Data Items to MEMs in GES | Link | Dave Addison | Xoserve | Elise Handy | 2022-09-29 | 2b (Cat 2 products with technical impacts) |  | High | 158 | Self-Governance | Technical Expert Panel | Gas | Suppliers, Metering Equipment Managers, GES Provider | 2023-02-24
R0078 | EMR Settlement Limited - additional access to EES | Link | Ben Lathbury | EMRS | Task Force Gemma Dixon | 2022-10-07 | 1a (Cat 1 products without technical impacts) |  | Medium | 111 | Self-Governance | Technical Expert Panel | Electricity | EMRS | 2023-09-29
R0084 | Housekeeping changes to the approved legal text for R0047 | Link | Ann Perry | Code Manager | Ann Perry | 2022-12-16 | 1a (Cat 1 products without technical impacts) |  | Low | 78 | Self-Governance | Change Panel | Electricity and Gas | MEMs, DNOs, Suppliers, AMI, MI and AMR Service Providers | 2023-04-01
R0088 | Make Shipper NExA values available on the GES portal | Link | Sharon Dudley | Xoserve | Elise Handy | 2023-01-12 | 2b (Cat 2 products with technical impacts) |  | Medium | 101 | Self-Governance | Technical Expert Panel | Gas | Gas Shippers, Gas Transporters, IGTs | 2023-11-03
R0090 | Alignment of Data Specification with Pre-REC Rules and Consequential Impacts on R0011 Legal Text | Link | Rosalind Timperley | Code Manager | Gemma Dixon | 2023-01-18 | 2b (Cat 2 products with technical impacts) |  | Low | 91 | Self-Governance | Technical Expert Panel | Electricity | Energy Suppliers, Generators and Capacity Providers | 2023-06-30
R0091 | Clarifications to the Theft Detection Incentive Scheme. | Link | Andrew Waghorn | Code Manager | Elise Handy | 2023-01-23 | 1a (Cat 1 products without technical impacts) |  | Low | 87 | Self-Governance | Change Panel | Electricity and Gas | Energy Suppliers | 2023-04-01
R0101 | Revision of the Implementation Date and approved solution for R0021 | Link | Tina Pearce | Code Manager | Colette Baldwin | 2023-03-23 | 2b (Cat 2 products with technical impacts) |  | High | 159 | Self-Governance | Metering Expert Panel | Electricity | EES, Electricity Suppliers, Meter Equipment Managers, Distribution Network Operators | 2023-06-30
R0102 | Revision of the approved solution for R0032 | Link | Ann Perry | Code Manager | Gemma Dixon | 2023-03-23 | 2b (Cat 2 products with technical impacts) |  | Medium | 133 | Self-Governance | Technical Expert Panel | Electricity | Suppliers, Metering Equipment Managers, Distribution Network Operators | 2023-06-30
R0103 | Central provision of DCC Technical Contacts for requesting test certificates | Link | Beth Brown | Code Manager | Task Force Colette Baldwin | 2023-03-23 | 1b (Cat 1 products with technical impacts) |  | High | 153 | Self-Governance | Change Panel | n/a | Switching Operator, CSS Users, Switching Data Service Providers | 2024-02-23
R0110 | A review of Supplier access to data on GES | Link | Lorna Mallon | Scottish Power | Lydia Bentley | 2023-04-13 | 1a (Cat 1 products without technical impacts) |  | Medium | 108 | Self-Governance | Technical Expert Panel | Gas | Suppliers, GES Provider | 2023-11-03
R0114 | Housekeeping amendments | Link | Ann Perry | Code Manager | Ann Perry | 2023-04-19 | 1a (Cat 1 products without technical impacts) |  | Low | 32 | Self-Governance | Change Panel | n/a | REC Parties | 2023-06-30
R0118 | Review of Schedule 12 and processes to manage access to data | Link | Katie Taaffe | RECCo | Task Force | 2023-05-12 | 1a (Cat 1 products without technical impacts) |  | Medium | 136 | Self-Governance | Change Panel | Electricity and Gas | RECCo, Code Manager | 2023-12-06
R0128 | Removal of CSS Business Rule 1177 to reflect OFAF optionality | Link | Mark Pearce | Code Manager | Harriet Truss | 2023-06-16 | 1a (Cat 1 products without technical impacts) |  | Medium | 103 | Self-Governance | Technical Expert Panel | Electricity and Gas | Switching Operator, Code Manager | 2023-12-06
R0136 | Change to REC Schedule 22 Market Stabilisation Charge (MSC) | Link | Lynne Fallon | RECCo | Sam Briggs | 2023-06-29 | 1a (Cat 1 products without technical impacts) |  | Medium | 113 | Self-Governance | Change Panel | Electricity and Gas | Suppliers, Code Manager | 2023-12-06
R0138 | Combined progression of Change Proposals R0058, R0104 and R0129 R0138 | Link | Elise Handy | Code Manager | Task Force Elise Handy | 2023-08-04 | 1a (Cat 1 products without technical impacts) |  | Low | 66 | Self-Governance | Change Panel | Electricity and Gas | Suppliers, Code Manager, RECCo | 2023-11-03
R0140 | Housekeeping - November Release | Link | Holly Law | Code Manager | Holly Law | 2023-08-04 | 2a (Cat 2 products without technical impacts) |  | Low | 70 | Self-Governance | Change Panel | Electricity and Gas | REC Parties | 2023-11-03
R0149 | Updates to the EES API Interface Specification | Link | Elise Handy | Code Manager | Task Force Elise Handy | 2023-10-20 | 2a (Cat 2 products without technical impacts) |  | Low | 68 | Self-Governance | Technical Expert Panel | Electricity | EES Users | 2023-12-06
R0156 | Updates to the CSS Message Business Data Validation Rules and Physical Interface Design Specification | Link | Caroline Milner | Code Manager | Holly Law | 2023-12-14 | 2a (Cat 2 products without technical impacts) |  | Low | 73 | Self-Governance | Technical Expert Panel | Gas and Electricity | CSS and CSS Users | 2024-02-23
R0093 | Uplift to CSS Maximum Demand Volumes during MHHS Migration Period | Link | Jon Hawkins | RECCo | Harriet Truss | 2023-02-06 | 2b (Cat 2 products with technical impacts) | No | High | 168 | Self-Governance | Technical Expert Panel | Electricity | Switching Operator, ERDS Providers, CSS Users, MHHS Programme | 2024-03-28
R0147 | Prepayment Levelisation | Link | Jon Dixon | RECCo | Harriet Truss | 2023-09-22 | 1a (Cat 1 products without technical impacts) | Yes | Critical | 193 | Authority-Approval | Change Panel | Electricity and Gas | Energy Suppliers | 2024-03-28
R0154 | Performance Assurance Report Catalogue V5.1 | Link | Lewis William | Code Manager | Lydia Bentley | 2023-11-08 | 2a (Cat 2 products without technical impacts) | No | Medium | 128 | Self-Governance | Performance Assurance Board | Electricity and Gas | Energy Suppliers, Gas Transporters, MEMs and DNOs | 2024-03-28
R0159 | Housekeeping Amendment to the PARC | Link | Holly Law | Code Manager | Holly Law | 2024-03-07 | 2a (Cat 2 products without technical impacts) | No | N/A | N/A | Self-Governance | Performance Assurance Board | Gas and Electricity | N/A | 2024-03-28
R0062 | Removal of ERDA meteringPointEnergyFlow change restriction | Link | Daniel Tadecicco | St Clements | Harriet Truss | 2022-08-11 | 1b (Cat 1 products with technical impacts) | No | Medium | 115 | Self-Governance | Change Panel | Electricity | DNOs, Suppliers, ERDS | 2024-04-12
R0063 | Addition of key information to all Service Now tickets | Link | Chris Price | St Clements | Elise Handy | 2022-08-22 | 1b (Cat 1 products with technical impacts) | No | Medium | 124 | Self-Governance | Technical Expert Panel | n/a | Switching Data Service Providers, Central Switching Service Provider | 2024-04-12
R0139 | Alignment of Market Message D0225 ‘consent to share flag’ to support PSR data sharing | Link | Katie Stanyard | Energy Networks Association | Holly Law | 2023-08-09 | 2b (Cat 2 products with technical impacts) | Yes | High | 168 | Self-Governance | Metering Expert Panel | Electricity | Suppliers, DNOs, MEMs | 2024-04-12
Note on L12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was Self-Governance then moved to Authority
Note on M12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Originally MEP - Change Panel after send back
Note on L50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed to self governance after it was agreed that a deferral was not going to be progressed

## Withdrawn
Last updated: 26/04/2024
Change Proposal Reference | Change Proposal Title | Link to CP page | Proposer Name | Proposer Company | Lead Analyst | Date Submitted | Change Category | Urgent (Y/N) | Priority Status | Priority Score | Change Path | Responsible Committee | Fuel | Impacted Parties | Withdrawl Date
R0004 | Electricity Enquiry Service (EES) Master Administration User (MAU) Access | Link |  | Scottish Power Energy Retail | Jonathan Holland | 2021-09-02 | 2b (Cat 2 products with technical impacts) | No | n/a | n/a | Self-Governance | Technical Expert Panel | Electricity | Suppliers, Network Parties, Metering Equipment Managers (electricity only), EES users | 2022-01-21
R0005 | Access to EES (Energy Enquiry Service) and GDCC API for CSS Interface Providers | Link | Karen Lee | ESG Global Ltd | Ann Perry | 2021-09-06 | 2b (Cat 2 products with technical impacts) | n/a | n/a | n/a | Self-Governance | Change Panel | n/a | No impacted parties | 2021-10-04
R0007 | Changes to message ownership in SDEP | Link | Rachel Norberg | Utilita | Jonathan Holland | 2021-09-08 | 2b (Cat 2 products with technical impacts) | No | n/a | n/a | Self-Governance | Technical Expert Panel | n/a | No impacted parties | 2021-12-06
R0013 | Electricity Enquiry Service API Service Status | Link | Andrew Long | Switchcraft | Jonathan Holland | 2021-10-08 | 2b (Cat 2 products with technical impacts) | No | n/a | n/a | Self-Governance | Technical Expert Panel | Electricity | n/a | 2022-01-14
R0016 | Resolution of Bilateral Erroneous Transfers | Link | Ben Atkinson | British Gas | Gemma Dixon | 2021-11-17 | 1b (Cat 1 products with technical impacts) | No | Low | 61 | Self-Governance | Change Panel | Electricity and Gas | Energy Suppliers, EES Provider | 2023-05-16
R0024 | EAC information in the EES API | Link | Andrew Long | Switchcraft | Jonathan Holland | 2021-12-10 | 2b (Cat 2 products with technical impacts) | No | n/a | n/a | Self-Governance | Technical Expert Panel | n/a | Energy Suppliers, EES Users | 2022-08-29
R0026 | Whole current (WC)/Current Transformer (CT) certificates | Link | Courtney Campbellwood | Code Manager | Task Force Elise Handy | 2022-01-06 | 1a (Cat 1 products without technical impacts) | No | Medium | 103 | Self-Governance | Metering Expert Panel | Electricity | Metering Equipment Managers | 2023-12-13
R0027 | Minimum identification requirements in the Meter Operation Code of Practice | Link | Courtney Campbellwood | Code Manager | Courtney Campbellwood | 2022-01-06 | 1a (Cat 1 products without technical impacts) | No | n/a | n/a | Self-Governance | Metering Expert Panel | n/a | n/a | 2022-04-09
R0029 | Mandating Timely Meter Product Data (MPD) Updates | Link | Rosalind Timperley | Code Manager | Ann Perry | 2022-01-11 | 2a (Cat 2 products without technical impacts) | No | n/a | n/a | Self-Governance | Change Panel | n/a | n/a | 2022-02-18
R0040 | CSS Switch Synchronisation to ERDA at SecuredActive | Link | Daniel Tadecicco | St Clements | Harriet Truss | 2022-03-16 | 1b (Cat 1 products with technical impacts) | No | Medium | 121 | Self-Governance | Change Panel | n/a | All REC Parties | 2022-11-02
R0046 | Governance of Data under the REC | Link | Brian O'Shea | RECCo | Jonathan Holland | 2022-05-20 | 1a (Cat 1 products without technical impacts) | Yes | n/a | n/a | Authority-Approval | Change Panel | n/a | Energy Suppliers, Gas Transporters, DNOs, Metering Equipment Managers and Non-REC Party Service Users | 2022-07-04
R0050 | Clarification of REC Maintenance of Qualification Schedule | Link | Bryan Heap | Electricity North West Limited | Ann Perry | 2022-05-17 | 1a (Cat 1 products without technical impacts) | No | Low | 88 | Self-Governance | TBD | n/a | No impacted parties | 2022-10-28
R0051 | Switch Request Objections (Change of Occupier) | Link | Simon Askew | Business Energy Direct | Task Force Elise Handy | 2022-05-24 | 1a (Cat 1 products without technical impacts) | No | Low | 70 | Self-Governance | Change Panel | n/a | Suppliers, TPIs. | 2024-01-12
R0057 | Clarification of Supplier of Last Resort Obligations under the REC | Link | Paul Saker | EDF | Elise Handy | 2022-07-15 | 2a (Cat 2 products without technical impacts) | No | Low | 48 | Self-Governance | Change Panel | Electricity and Gas | Energy Suppliers, Metering Equipment Managers, Data Collectors, Data Aggregators | 2023-08-04
R0058 | REC Services Procurement Clarification | Link | Cordelia Grey | DCC | Task Force Elise Handy | 2022-07-26 | 1a (Cat 1 products without technical impacts) | No | Low | 27 | Self-Governance | TBD | Electricity and Gas | DCC, RECCo | 2023-10-04
R0061 | Resolution of invalid CSS data by Data Owners | Link | Daniel Tadecicco | St Clements | Lydia Bentley | 2022-08-11 | 1b (Cat 1 products with technical impacts) | No | Medium | 118 | Self-Governance | Technical Expert Panel | Electricity | DNOs/iDNOs, Suppliers. MEMs, Switching Service Desk, MPRS | 2024-03-04
R0065 | Registration of Smart Export Guarantee (SEG) Sites | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2022-08-22 | 1a (Cat 1 products without technical impacts) | No | Low | 90 | Self-Governance | TBD | TBD | TBD | 2023-10-23
R0075 | Enabling Software Product Qualification | Link | Elaine Eyles | ESG Global Ltd | Task Force Elise Handy | 2022-10-07 | 1b (Cat 1 products with technical impacts) | No | Low | 42 | Self-Governance | TBD | Electricity and Gas | All REC Parties | 2024-03-11
R0077 | Resolution of EES API SearchAddress method discrepancies | Link | Mark Pearce | Code Manager | Jonathan Holland | 2022-10-13 | 2b (Cat 2 products with technical impacts) | No | Low | 43 | Self-Governance | n/a | n/a | No impacted parties | 2023-02-24
R0079 | Addition of Previous MEM to the EES API | Link | Adrian Salter | EDF | Task Force Caroline Freimuller | 2022-11-04 | 2b (Cat 2 products with technical impacts) | No | Low | 74 | Self-Governance | Technical Expert Panel | Electricity | MEMs | 2024-04-24
R0081 | CSS Market Message Retry Strategy | Link | Cordelia Grey | DCC | Task Force Elise Handy | 2022-10-27 | 2a (Cat 2 products without technical impacts) | No | Medium | 136 | Self-Governance | TBD | Electricity and Gas | CSS Provider, EES, GES | 2023-11-01
R0082 | Formalising the Submission of PPMIP Unallocated Transaction Report (UTR) Files | Link | Rosalind Timperley | Code Manager | Task Force Elise Handy | 2022-11-28 | 1a (Cat 1 products without technical impacts) | No | Low | 57 | Self-Governance | Change Panel | Electricity | EES Provider | 2024-03-22
R0085 | Switching Programme Designation of the Steady State Commencement Date | Link | Tina Pearce | Code Manager | Ann Perry | 2022-12-16 | 1a (Cat 1 products without technical impacts) | No | Low | 32 | Self-Governance | TBD | n/a | No impacted parties | 2023-05-16
R0086 | ERDS Upload File in the Data Specification and clarification of cancellation code | Link | Ryan Dale | Code Manager | Task Force Elise Handy | 2022-12-16 | 2b (Cat 2 products with technical impacts) | No | Low | 64 | Self-Governance | TBD | Electricity | ERDS, EES | 2023-10-23
R0089 | Removal of Pre-COVID AQ Value from Data Access Matrix | Link | Dave Addison | Xoserve | Task Force Elise Handy | 2022-12-30 | 2a (Cat 2 products without technical impacts) | No | Low | 32 | Self-Governance | TBD | Gas | Suppliers | 2024-01-05
R0104 | Clarifying requirement for continuous billing following an Erroneous Switch | Link | Jon Hawkins | RECCo | Task Force Elise Handy | 2023-03-28 | 1a (Cat 1 products without technical impacts) | No | Low | 84 | Self-Governance | TBD | Electricity and Gas | Energy Suppliers | 2023-10-04
R0106 | Performance Assurance Report Catalogue V5.1 | Link | Lewis Williams | Code Manager | Task Force Elise Handy | 2023-04-04 | 1a (Cat 1 products without technical impacts) | No | Low | 63 | Self-Governance | TBD | Gas and Electricity | All REC Parties | 2023-11-01
R0107 | CSS Message Time Stamping | Link | Leo Brown | DCC | Task Force Elise Handy | 2023-04-06 | 2b (Cat 2 products with technical impacts) | No | Medium | 107 | Self-Governance | TBD | Gas and Electricity | CSS Users | 2023-08-11
R0109 | Aligning electricity and gas timescale requirements for sharing Meter Technical Detail information | Link | Sarah Barry | Utility Warehouse | Task Force Elise Handy | 2023-03-06 | 1a (Cat 1 products without technical impacts) | No | Low | 68 | Self-Governance | TBD | Electricity and Gas | MEMs, Energy Suppliers, EES, GES | 2024-02-08
R0112 | Supplier compensation for Network Party driven MPXN or GSP Group changes | Link | Lorna Mallon | Scottish Power | Task Force Elise Handy | 2023-03-27 | 1a (Cat 1 products without technical impacts) | No | Low | 33 | Self-Governance | TBD |  |  | 2023-07-28
R0117 | Retrospective Implementation of Distribution Code Use of System Agreement (DCUSA) DCP 383 | Link | Colette Baldwin | Code Manager | Task Force Elise Handy | 2023-05-12 | 1a (Cat 1 products without technical impacts) | No | Medium | 141 | Self-Governance | Metering Expert Panel | Electricity | MEMs | 2023-11-17
R0127 | New EES User Category for the Department for Education | Link | Kathryn Swanson | Department for Education | Task Force Elise Handy | 2023-06-13 | 1a (Cat 1 products without technical impacts) | No | Low | 99 | Self-Governance | TBD | Electricity | No impacted parties | 2024-04-05
R0129 | Clarifying Event of Default requirements | Link | Anton Moden | Code Manager | Task Force Elise Handy | 2023-06-08 | 1a (Cat 1 products without technical impacts) | No | Low | 87 | Self-Governance | TBD | Electricity and Gas | All REC Parties | 2023-10-04
R0132 | Change the Logical Format of the J0001 (DI50001) ‘Market Participant Role Code’ data item to Char(2) | Link | Colin Berry | Elexon | Holly Law (with Harriet Support | 2023-06-22 | 2b (Cat 2 products with technical impacts) | No | Critical | 188 | Self-Governance | Technical Expert Panel | Electricity | Suppliers, MEMs, DNOs, ERDS providers, EES, SDES & GDCC provider | 2023-10-20
R0133 | Consequential Cross-Code Change for BSC P441 - Complex Site Classes Creation | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2023-07-04 | 1a (Cat 1 products without technical impacts) | No | High | 163 | Self-Governance | Metering Expert Panel | Electricity | Suppliers/MEMs/DNOs | 2024-03-08
R0134 | VLP data access requirements | Link | Roxanne Inskip-Kaye | Levelise Limited | Task Force Elise Handy | 2023-06-30 | 2b (Cat 2 products with technical impacts) | No | HIgh | 160 | Self-Governance | Technical Expert Panel | Electricity | EES Provider, VLPs | 2024-03-08
R0135 | Add DESNZ to Schedule 12 | Link | Jasmin Prya Wade | DESNZ | Task Force Elise Handy | 2022-12-15 | 2b (Cat 2 products with technical impacts) | No | High | 154 | Self-Governance | Technical Expert Panel | Electricity and Gas | No impacted parties | 2024-03-08
R0141 | Recommended Data Access Matrix changes due to Data Permission Matrix changes | Link | David Addison | Xoserve | Task Force Elise Handy | 2023-05-31 | 1a (Cat 1 products without technical impacts) | No | Low | 98 | Self-Governance | Technical Expert Panel | Gas | GES Users | 2023-09-04
R0151 | Implementation of Online Certificate Standard Protocol (OCSP) in addition to Certificate Revocation List (CRL). | Link | Stuart Pitcher | DCC | James Hardy | 2023-06-21 | 1a (Cat 1 products without technical impacts) | No | Medium | 110 | Self-Governance | Change Panel | Electricity and Gas | CSS Users | 2024-04-24
Note on M41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: May change under new process R0118.

## Rejected
Last updated: 26/04/2024
Change Proposal Reference | Change Proposal Title | Link to CP page | Proposer Name | Proposer Company | Lead Analyst | Date Submitted | Change Category | Urgent (Y/N) | Priority Status | Priority Score | Change Path | Responsible Committee | Fuel | Impacted Parties | Rejected Date
R0009 | Introduction of SDEP and EES User Maintenance API | Link | Jonathan Holland | Code Manager | Jonathan Holland | 2021-09-08 | 2b (Cat 2 products with technical impacts) | No | Low | 83 | Self-Governance | Technical Expert Panel | Electricity and Gas | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers, EES Users | 2023-08-24
R0068 | REC Main Body Data Protection Changes | Link | Bradley Baker | DCC | James Hardy | 2022-09-02 | 1a (Cat 1 products without technical impacts) | No | Low | 83 | Self-Governance | Change Panel | n/a | DCC | 2024-03-19
R0083A | Changes to Supply Number Format for MHHS (Alternative) | Link | Andrew Wallace | RECCo | Harriet Truss | 2022-12-05 | 2a (Cat 2 products without technical impacts) | No | High | 158 | Authority-Approval | Change Panel | Electricity | Suppliers, DNOs, TPIs, EES | 2023-11-17
R0143 | New value for Site Visit Check Code (J0024) | Link | Peter Waymont | UK Power Distribution | Colette Baldwin | 2023-04-17 | 2b (Cat 2 products with technical impacts) | No | High | 162 | Self-Governance | Metering Expert Panel | Electricity | DNOs/Suppliers | 2024-02-27
R0145 | Service Termination Issue Reporting | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2023-08-21 | 2a (Cat 2 products without technical impacts) | No | High | 167 | Self-Governance | Metering Expert Panel | Electricity | DNOs/MEM/Suppliers | 2024-02-14
R0111 | Provision of Grid Supply Point Group ID from a Postcode search | Link | Andrew Dawson | GB Group Plc | Task Force Elise Handy | 2023-04-18 | 2b (Cat 2 products with technical impacts) | No | Low | 68 | Self-Governance | TBD | Electricity | Third Party Intermediaries | 2024-04-05